## Summary
Project planning for NCUR is divided into 4 different groups in order to increase stakeholder engagement and deliverable progress:
Group | Purpose
Executive Committee | This committee consists of the president and high-level executives. They meet when there is information that needs to be communicated/approved by that level. We believe this will be respectful of their time as they will not need to attend the detailed meetings and the entire meeting would be dedicated to presenting information relevant to them and their level.
Steering Committee | This committee consists of the chairs of all of the committees plus the project managers (Elizabeth and Amanda) and the project leads (Amy and Chris). This committee meets bi-weekly and is responsible for reviewing all of the decisions from the subcommittees and would allow for some cross-communication between the committees.
Subcommittees | This group of committees are each charged with a specific facet of the conference. This allows for a dedicated working group for key project deliverables.
NCUR Milestone Meeting | This group is a combination of people across campus who are invested in NCUR and meets bi-monthly. In these meetings we discuss cross-subcommittee information, any issues that arise that need group discussion, and any presentations could occur that need more than the steering committee’s eyes. This allows for all project team members to receive communication at the high project level so everyone is on the same page.

## Executive Committee
Executive Committee
Member Name | Represented Area
Pamela Whitten | President
Ron Matson | Provost
Don McGarey | VP for Research
Brenda Stopher | Special Assistant to the President
Rita Bailey | Representative from the Dean's Council
Chris Sanford | Representative from Chairs and Directors Assembly
David Stollberg | Representative from Faculty Senate
Alex McGee | VP for External Affairs and Chief of Staff
Alice Wheelwright | Associate Vice President of Strategic Communications and Marketing
Amy Buddie | Core Team
Chris Cornelison | Core Team
Elizabeth Starnes | Core Team
Amanda Leith | Core Team

## Steering Committee
Steering Committee
Member Name | Represented Area
Pamela Whitten | KSU President
Amy Buddie | NCUR Lead, Final Report Committee chair, Accommodations Committee chair, Plenary Speakers and Presentations Committee chair
Chris Cornelison | NCUR Second Lead, Food Committee chair
Zachary Kerns | Budget and Finance Committee chair, Registration and On-Site Logistics Committee chair
Michael Sanseviro | Campus Engagement Committee chair
Ron Ramos | Communications and Information Committee chair
Mary Quat | Sponsorships Committee chair
Ryan Keesee | Conference Volunteers Committee chair
Erik Malewski | Diversity and Inclusion Committee co-chair
Nathalia Jaramillo | Diversity and Inclusion Committee co-chair
Maureen Patton | Excursions, Social Events, NCUR Oversight, Professional Preparation Fair Committee chair
Matthew Robison | Special Activities Committee chair
Jim Herbert | Technology Logistics Committee chair, Mobile App & Program Committee chair
Fola Teru | Facilities Committee co-chair
Jenny Morris | Facilities Committee co-chair
Edward Stephens | Public Safety and Risk Management Committee co-chair
Andy Altizer | Public Safety and Risk Management Committee co-chair
Lee White | Transportation and Parking Committee co-chair
Julia Allison | Transportation and Parking Committee co-chair
Elizabeth Starnes | Project Management
Amanda Leith | Project Management
John Marshall | Legal
Note: Currently not represented: Career Fair Committee, Presentations Committee, Abstract Review Committee

## Subcommittees
NCUR Subcommittee List
Committee Name | Committee Chair | Committee Members (Note: Amy, Chris, Elizabeth & Amanda will be invited to all) | Start Date | Meeting Time | Description | Notes
Abstract Review Committee | Dean/VP Level - AAF (Ron Matson?) | Heads of Departments (faculty members). Amy will send the entire list as separate email and this will need to be a separate tab. Jen Purcell- faculty senate Karen Boettler | Start in June for Chair but then not hold meetings until Sept. to decide on review criteria |  | Review student and FAN abstracts. Recruit, secure, and assist faculty reviewers for abstracts. After the review period, provide assistance to the Presentation committee. | Amy/Chris will reach out to Dr. Matson.
Food Committee | Chris Cornelison | Amy Rhodes, Brian Jones, Maureen Patton, Sally Bullard, Zachary Kerns, Megan Max, Jen Duggan, Christian Hardigree, Jordan Barron, Kate Newberry | June 2018 |  | Coordinates food and beverage for the conference and events related to the conference (social events)
Budget and Finance Committee | Zachary Kerns | Kristin Evans, Don McGarey, Madhavi Rajdev, Cheryl Hassman, Mary Quat | ASAP then monthly until december then biweekly |  | Manage all financial aspects of NCUR budget, revenue, and expenses.
Campus Engagement Committee | Michael Sanseviro | Tsai-Tien Tseng, AAF?, Kimberly Hengold, Chris Hutt, Matthew Robison, Veronica Trammell | April 2018 |  | Coordinate student interest sessions, campus open houses
Communications and Information Committee | Ron Ramos | Tammy Demel, Jason Pless, Tim Falvai, PM, Amy Buddie, Chris Cornelison, Jennifer Leifheit-Little, Thomas Dale | In Progress | biweekly, starting 5/7 (really need that week): best time for ron, tammy, jason and tim is Fridays at 3:00 pm, in the marketing conference room (TP2500) | Manage conference communications (help lines, signage, website, social media, & information tents). Assist the Public Relations and Marketing committee with informing and marketing NCUR 2018 to external stakeholders (campus, state and nation). | This will have to work closely with Mobile App committee. Use the student assitant who's doing the mobile app to help with the help line. We could also potentially use the service desk for tier 1 support- use a separate number so they new it was a NCUR question.
Sponsorships Committee | Mary Quat | Development officers | In Progress | Every Tuesday at 2pm | Obtain corporate and community sponsorships. Works with Communications and Information Committee to inform and market NCUR 2018 to campus, Kennesaw and national audience.
Conference Volunteers Committee | Ryan Keesee | Thomas Yannuzzi, Lindsay Johnson, Christian Hardigree, Student Life, Staff Senate rep, Residence Life (Jeff Cooper or Natalie Reckard), Alumni Affairs -- Pierette Maillet, Student Rec, Thomas Dale | April 2018 |  | Recruit, schedule, and organize student, faculty, & staff volunteers from KSU and surrounding predominantly undergraduate institutions (PUIs). | IT will have some volunteers. Hospitality will give credit to their students for being volunteers and those hours are required for graduation. We do have the volunteer breakdown now. Do people volunteer for a specific job or do you volunteer in general and then you are assigned somewhere. Also includes volunteer training. If you're a faculty member, you get different questions than staff/student. Question to ask at OK.
Diversity and Inclusion Committee | Erik Malewski/Nathalia Jaramillo | Matthew Foley, Charles Dickens, Loretta Daniels, Jennifer Wilson, Jordan Cameron, Seneca Vaught, Thomas Yannuzzi | Meet in April to discuss, then ask how/when they want to be involved |  | Promote diversity and inclusion at the conference, increase participation from underrepresented groups. Oversee campus sustainability and ADA compliance before and during the conference. | Need a kick off meeting to brainstorm how they can help. Perhaps they are a review/oversight committee?
Final Report Committee | Amy Buddie | Chris Cornelison, Don McGarey, Zachery Kerns, Tim Falvai | May 2019 |  | Collect steering committee reports, statistics, and additional conference data to develop, print, and distribute the NCUR 2018 final report. | Have in committee responsibilities, give the template, remind them regularly, but this committee doesn't meet regularly until after the event
Excursions, Social Events, NCUR Oversight, Professional Preparation Fair Committee | Maureen Patton | Sally Bullard, Zachery Kerns, Jennifer Leifheit-Little, Anna Tucker, Stephanie Green, Brian Wooten, Joe Skopitz, Hannah Gordon, and Christin Richardson | May 7th |  | Plan, oversee, and administer NCUR Excursions and campus social events (Big Event at the Cox Center, Thursday Night @ the Nigh). Coordinate with the NOC and the NCUR 2018 chair and co-chair to plan and execute the October 2017 and April 2018 NOC visits and dinner receptions. Plan and execute the Graduate and Professional Studies for conference participants. | For Professional Preparation Fair part - Set up somewhere near the poster session. Other Graduate Colleges know about this and go to NCUR every year. We need to make sure it is organized and parking/location is set up. Huge money maker for the conference.
Special Activities Committee | Matthew Robison | Sally Bullard,Sandefur Porter, Tara Parker, Dr. Barbre Berris, Matt LaStar, Katherine Bass, Stephen Ho, Jenny Brown, Christian Hardigree, Jieron Robinson | start thinking but start meeting in july |  | Planning fun events on campus for students to enjoy all of campus and meet KSU student groups.
Technology Logistics Committee | Jim Herbert | Davide Gaetano, Jonathan Higgins, Stephen Gay, Veronica Trammell, Jennifer Leifheit-Little, Mansour Abusaid, Christina Coronado, Cheryl Hassman, Thomas Dale, Matt LaStar, Michaël Pourreau, Amy Buddie, Chris Cornelison, Amanda Leith, Elizabeth Starnes, Michael Lenna and Adam Tilley | April 2018 |  | Oversee and assist with campus technology to make sure tech needs are met for the event, including registration technology, but not including mobile app (that is being broken out). | This will be before and during the conference.
Plenary Speakers and Presentations Committee | Amy Buddie | Tammy Demel, Mary Quat, Chris Cornelison, Alex McGee, Brandon Harris, Jennifer Leifheit-Little, Jeremy Walts, Jim Herbert, Matthew LaStar | April 2018 |  | Recruit plenary speakers and schedule speaking events during conference, ensure speakers arrive and have accommodations for the conference. Student speakers to open plenary sessions. Recruits and secures faculty moderators- breakout committee
Mobile App & Program Committee | Jim Herbert | Ron Ramos, Jason Pless, Chris Ward, Amos Williams, (Temp employee- for NCUR), Davide Gaetano, Thomas Dale, Michael Pourreau, Thomas Yannuzzi | April 2018 |  | Prepare and write mobile app content and online conference program for all participants, utilize teams to gather information from all committees, determine digital program needs and access. Backend registration and on-site check in/badging/scanning technology. | The employee will have to focus on this for a few months.
Registration and On-Site Logistics Committee | Zachary Kerns | Jim Herbert, Scott Bassford, Christina Coronado, (Jonathan Higgins), Tim Carver, Lisabeth Hames, whole Department of Event and Venue Management | May 7th |  | Manage front-end, legistical, non IT aspects of conference and workshop registration including the online submission, airport and campus on site check-in. (badge check in)
Facilities Committee | Fola Teru, Jenny Morris | Public Safety, Michael Fellows, Zachary Kerns, Joe Skopitz, Jennifer Wilson, Julia Allison |  |  | Oversee readiness and perform institutional assessment of campus and preparations for the NCUR conference with continual management of buildings and conference needs during event, and assisting colleges and directors with building improvements.
Accommodations Committee | Amy Buddie | Jennifer Harb, Diane Lovett (Cobb Toursim and Travel) | March 2018 | Secure conference hotels | Secure conference hotels
Presentations Committee | Amanda Leith | Nicole Sherrod, Veronica Trammell, Thomas Yannuzzi, PM scheduler?, Tara Parker | January 2019 (only after acceptances) | Aid in planning poster, oral presentation, arts, and Faculty-Administration Network (FAN) sessions (develop schedule, assign rooms, etc.). | Aid in planning poster, oral presentation, arts, and Faculty-Administration Network (FAN) sessions (develop schedule, assign rooms, etc.). | Devote them 100% to this task for 2 weeks
Public Safety and Risk Management Committee | Edward Stephens/ Andy Altizer | Tim Murphy, Robert Milam, James Westbrook, Stephen Gay, Bob Williams, Meg Bowles |  | Perform risk assessment of all planned activities and campus locations and mitigate any and all hazards associated with public safety. During conference, oversee main communications hub for public safety and weather precautions. | Perform risk assessment of all planned activities and campus locations and mitigate any and all hazards associated with public safety. During conference, oversee main communications hub for public safety and weather precautions.
Transportation and Parking Committee | Lee White/Julia Allison | Lt. Milam, C Murphy, Julie Wilson, Girma Mamo, Kelley Wisniewski, DJ Gilliland, Erica Massicot |  | Secure buses for participant shuttles from airport to lodging and conference sites; plan on-campus transportation for participants with disabilities, and plan and coordinate parking logistics for conference shuttles, participants, and campus faculty and staff. | Secure buses for participant shuttles from airport to lodging and conference sites; plan on-campus transportation for participants with disabilities, and plan and coordinate parking logistics for conference shuttles, participants, and campus faculty and staff. | Do they need volunteers?
Grad & Career Fair Committee | Mark Forehand | Amanda Long, Loretta Daniels, Julia Allison, Chelsea Law | April 2018 | NCUR attendees get free admission to the GA Career Fair (the day before- Wed 4/10) | NCUR attendees get free admission to the GA Career Fair (the day before- Wed 4/10) | Confirm if it should be a committee. Amy already reached out about if the career fair was happening.

## NCUR Milestone
NCUR Milestone Meeting
Member Name | Position Title
Aaron Fowler | Director of Parking & Transportation
Alice Wheelwright | Associate Vice President of Strategic Communications and Marketing
Amanda Leith | IT Project Manager
Amanda Rhodes | Director of Catering
Amy Buddie | Director of Undergraduate Research and Professor of Psychology
Brenda Stopher | Special Assistant to the President
Brian Jones | Campus Executive Chef
Brian Wooten | Executive Director of Community Engagement
Chris Hutt | Assistant Vice President
Christopher Cornelison | Assistant Director of Undergraduate Research
Dianne Summey | Business Operations, Office of the President
Donald McGarey | Interim Vice President for Research
Edward Stephens | Chief of Police
Elizabeth Starnes | Executive Director, IT Project Management Office
Jason Pless | Marketing Specialist
Jennifer Leifheit-Little | Video Services
Jim Herbert | Interim Chief Technology Officer
Jodie Sweat | Director of Plant Operations
Julia Allison | Associate Director of Parking Operations
Kasey Helton | Assistant Vice President of Auxiliary Services
Lee White | Associate Director of Transportation
Lori Howard | Secretary to the President
Mary Quat | Sr. Director of Foundation Relations
Matthew Robison | Director of Student Engagement
Maureen Patton | Director, University Events
Michael Sanseviro | Associate Vice President and Dean of Students & Dean of Student Success
Pamela Whitten | President
Paul Floeckher | Public Relations Specialist
Robert Milam | Police Lieutenant
Ronald Ramos | Assistant Vice President for Strategic Communications & Mktg
Ryan Keesee | Manager of Civic Engagement & Service Learning
Sally Bullard | Assistant Director, University Events
Tammy Demel | Asst VP, Strategic Comm & Issues Mgmt
Tim Murphy | Police Captain/Special Operations Commander
Veronica Trammell | Executive Director, LTAO
Zachary Kerns | Exec Dir, Events,Camps&Conf & General Mgr,Sprts/Rc